## Mitigate risks to lib service
Barnet Libraries Team Plan, Objective 1: Mitigate the risks to the service caused by the pandemic
No. | Barnet Plan objective | Barnet Plan objective | BP sub heading | BP sub heading | Risk | 3 Rs | What | Who (Lead) | Who | Who | Who | When | Progress | Progress Checks notes For P1 use
1 | Thriving |  | Helping people back into work |  | Slow pace of recovery affects library use | Reinvent | Develop volunteering strategy and introduce SSO volunteers when able. | CW | LCSMs | P0 | P2 | 2021-07-01 | started
2 | Clean, Safe and Well-Run |  | Improving customer services |  | Slow pace of recovery affects library use | Reinvent | NBA – investigate how opening hours can be extended in partnership with the leisure centre | HR/RP | NB |  |  | 2021-07-01 | Open
3 | Clean, Safe and Well-Run |  | Improving customer services |  | Slow pace of recovery affects library use | Reinvent | Here to Help newly named ‘Discover Your Library’ to support customers to come back; induction sessions for new members, outreach visits to promote services | LMT | LCSMs | P2 | P4 | 2021-07-01 | Open
4 | Clean, safe and Welll-Run |  | Improving customer services |  | Slow pace of recovery affects library use | Retain: | Use HLS/MOB to extend reach of S&C. | II |  |  |  | 2020-11-01 | completed
5 | Clean, safe and Welll-Run |  | Improving customer services |  | Changes in behaviour mean that customers don’t come back | Reinvent | Develop outreach strategy (link to IDP) | HR | LMT | P4 | CL/SG | 2021-05-01 | Open
6 | Clean, safe and Well-Run |  | Improving customer services | Improving digital access | Changes in behaviour mean that customers don’t come back | Reinvent | Develop online enquiries service | CL | SDL Team |  |  | 2020-11-01 | completed
7 | Clean, safe and Well-Run |  | Improving customer services |  | Changes in behaviour mean that customers don’t come back | Reinvent | Map existing partnerships and identify gaps | All Teams | P4 |  |  | 2021-05-01 | Open
8 | Clean, safe and Well-Run |  | Improving customer services |  | Changes in behaviour mean that customers don’t come back | Reinvent | Define customer segmentation for marketing and design campaigns to fit | CL/SG |  |  |  | 2021-05-01 | Open
9 | Clean, safe and Well-Run | Healthy | Improving customer services | Mental health & well-being | Changes in behaviour mean that customers don’t come back | Retain: | Continue S&C after libraries open for browsing and investigate volunteer support | CW | P2 | Ops |  | 2021-07-01 | Open
10 | Clean, safe and Well-Run |  | Robust financial management |  | Negative financial impact | Reinvent | Introduce mechanism for accepting donations. | P6 | HR | CL |  | 2021-05-01 | started
11 | Clean, safe and Well-Run |  | Robust financial management |  | Negative financial impact | Reinvent | Develop proposals for future income generation | LLL | P6 | HR |  | 2021-09-01 | Open
12 | Clean, safe and Well-Run |  | Robust financial management |  | Negative financial impact | Reinvent | Develop income strategy | LMT | P6 |  |  | 2021-09-01 | Open
13 | Clean, safe and Well-Run |  | Robust financial management |  | Negative financial impact | Reinvent | Revise room booking fees and charges | P6 |  |  |  | 2021-04-01 | completed
14 | Clean, safe and Well-Run |  | Robust financial management |  | Negative financial impact | Reinvent | Identify efficiencies in current budgets - Review grounds maintenance/ trade waste costs and revise requirements down | RP |  |  |  | 2021-06-01 | Open
15 | Clean, safe and Well-Run |  | Robust financial management |  | Negative financial impact | Reinvent | Submit inflation bid | HR |  |  |  | 2021-05-01 | Open
16 | Clean, safe and Well-Run |  | Robust financial management |  | Negative financial impact | Reinvent | Review use of waste and sani bins by tenants and billing arrangements | RP |  |  |  | 2021-06-01 | Open
17 | Clean, safe and Well-Run |  | Robust financial management | Improving customer services | Negative financial impact | Reinvent | Booking Live system for online booking and payment for events (bypassing My Account) | LMT |  |  |  | 2021-06-01 | started
18 | Thriving |  | Growth Strategy/ Town centres |  | Decline in the high street | Reinvent | Ensure library needs are reflected on the Infrastructure Development Plan and develop closer links with the Grwoth Team | HR |  |  |  | 2020-12-01 | started
19 | Thriving |  | Growth Strategy/ Town centres |  | Decline in the high street | Reinvent | Library Development plans created for all localities | RP | LCSMs |  |  | 2021-09-01 | Open
20 | Thriving |  | Growth Strategy/ Town centres |  | Decline in the high street | Reinvent | Link in to corporate ‘Live/shop local’ marketing campaigns | HR |  |  |  | 2021-05-01 | started
21 | Clean, safe and Well-Run | Healthy | Improving customer services | Mental health & well-being | Prolonged uncertainty leads to poor staff morale | Reinvent | Develop Technology forward plan | HR |  |  |  | 2021-06-01 | Open
22 | Healthy | Mental health & well-being |  |  | Prolonged uncertainty leads to poor staff morale | Reinvent | Establish Book Chat/ staff engagement events | CL | SG |  |  | 2020-12-01 | completed
23 | Clean, safe and Well-Run | Improving customer services | Healthy | Mental health & well-being | Prolonged uncertainty leads to poor staff morale | Reinvent | Deliver alternative conference/ investigate options | LLL |  |  |  | 2021-03-01 | started
24 | Clean, safe and Well-Run | Robust financial management | Improving customer services |  | Brexit leads to problems with suppliers and resources | Reinvent | Contact main suppliers to ensure plans in place for no deal Brexit (Capita Libraries, media suppliers) | CL |  |  |  | 2020-12-01 | completed
25 | Clean, safe and Well-Run | Robust financial management | Improving customer services |  | Brexit leads to staffing problems | Reinvent | Affected staff have appropriate settled status | HR |  |  |  | 2021-05-01 | Open
Note on K4: Richens, Hannah: Handbook on SSO volunteering
Note on L4: Richens, Hannah: Facebook ads and publicity
Note on K6: Richens, Hannah: Design badge/ t shirt
Note on L6: Richens, Hannah: Brainstorn what could be included in DyL sessions
Note on K8: Richens, Hannah: link to discover your library sessions
Note on L8: Richens, Hannah: link to comms strategy
Note on I10: Richens, Hannah: all teams to map existing contacts and partnerships
Note on J10: Richens, Hannah: design form
Note on M11: Richens, Hannah: start campaigns in early summer
Note on I12: Richens, Hannah: to be part of volunteer strategy
Note on J12: Richens, Hannah: publicity
Note on I13: Richens, Hannah: scope scheme and find examples, brainstoem business case
Note on J13: Richens, Hannah: to write business case and fees and charges paper
Note on K13: Richens, Hannah: contact Dipti re website implications
Note on I14: Richens, Hannah: include in 2021 conference. LMT to brainstorm parameters
Note on J14: Richens, Hannah: to brainstorm ideas
Note on K14: Richens, Hannah: to include in fees and charges paper
Note on I15: Richens, Hannah: Away day 1 June
Note on I19: Richens, Hannah: contact Sal Waheed
Note on J22: Richens, Hannah: identify local community groups including business groups eg. Love Burnt Oak (see link to outcome strategy)

## Impacts of the pandemic
Barnet Libraries Team Plan, Objective 2: Respond to the impact of the pandemic (customers and communities)
No. | Barnet Plan objective | Barnet Plan objective | BP sub heading | BP sub heading | Impact | 3 Rs | What | Who (Lead) | Who | Who | Who | When | Progress | Progress Checks notes For P1 use
1 | Thriving | Healthy | Growth Strategy | Impacts of Covid | Digital exclusion | Restore | Reinstate B&SC IT classes at HEN | KM | CL |  |  | 2020-11-01 | completed
2 | Thriving | Healthy | Growth Strategy | Impacts of Covid | Digital exclusion | Restore | Reinstate B&SC IT classes at CLN | KM | CL |  |  | 2021-07-01 | Open
3 | Clean, Safe and Well-Run | Heathy | Improving customer services | Impacts of Covid | Digital exclusion | Reinvent | Introduce remote IT support for customers | SM | Recovery Group |  |  | 2020-12-01 | completed
4 | Clean, Safe and Well-Run | Heathy | Improving customer services | Impacts of Covid | Digital exclusion | Reinvent | Roll out Windows 10 PCs | FPR |  |  |  | 2021-05-01 | Started
5 | Clean, Safe and Well-Run | Heathy | Improving customer services | Impacts of Covid | Digital exclusion | Reinvent | Funding application for laptop distribution | CL |  |  |  | 2020-12-01 | completed
6 | Healthy |  | Mental Health & Well-Being |  | Lonliness & social isolation | Reinvent | Develop online conversation cafes | Recovery Group |  |  |  | 2021-01-01 | completed
7 | Healthy |  | Mental Health & Well-Being |  | Lonliness & social isolation | Reinvent | Develop online reading groups/ facebook groups | Recovery Group |  |  |  | ? | open
8 | Healthy | Family Friendly | Mental Health & Well-Being | Life Chances | Lonliness & social isolation | Reinvent | Develop EY nuture groups | SG | Early Years |  |  | 2020-12-01 | completed
9 | Healthy |  | Mental Health & Well-Being | Maintaining Independence | Lonliness & social isolation | Reinvent | Develop Reading Friends groups | CL |  |  |  | 2021-01-01 | completed
10 | Healthy |  | Mental Health & Well-Being | Maintaining Independence | Lonliness & social isolation | Reinvent | Establish social prescribign routes to adult library services | RP |  |  |  | 2021-04-01 | Open
11 | Healthy | Family Friendly | Mental Health & Well-Being | Life Chances | Lonliness & social isolation | Reinvent | Establish social prescribign routes to child/ teen library services | SG |  |  |  | 2021-04-01 | Open
12 | All |  | All |  | Lonliness & social isolation | Retain | Retain programme of online events – planning 1 term ahead | CL | SG | RP | Ops Teams | 2020-11-01 | started
13 | Family Friendly |  | Education & Learning |  | Education & Learning | Reinvent | Develop virtual class visits | CL | EY |  |  | 2021-05-01 | started
14 | Family Friendly |  | Education & Learning |  | Education & Learning | Reinvent | Develop online STEAM events | CL | NM | Ops Teams |  |  | started
15 | Family Friendly |  | Education & Learning |  | Education & Learning | Reinvent | Submit bid to National Sience Week | SG |  |  |  | 2020-11-01 | completed
16 | Family Friendly | Thriving | Education & Learning | Growth Strategy | Education & Learning | Reinvent | Develop a Festival of Stories bid to ACE for 2022 | CL | SG |  |  | 2021-09-01 | Open
17 | Family Friendly |  | Education & Learning |  | Education & Learning | Reinvent | Review participation in national SRC for 2022 | CL | SDLs | P3 |  | 2021-09-01 | open
18 | Family Friendly |  | Education & Learning | Life Chances | Education & Learning | Reinvent | Meet with Neil Marlow to discuss how libraries can better support schools and recovery | CL | SG |  |  | 2021-05-01 | Open
19 | Family Friendly |  | Education & Learning | Life Chances | Education & Learning | Reinvent | Investigate adding lunch element to SRC 2021 | CL | SG |  |  | 2021-08-01 | started
20 | Family Friendly |  | Education & Learning | Life Chances | Education & Learning | Reinvent | Participate in London City of Stories 2021 | CL | SG | Ops Teams | Early Years | 2021-08-01 | Open
21 | Thriving | Healthy | Helping residents, especially young people into work | Impacts of Covid | Employment | Reinvent | Introduce Kickstart Trainees into libraries | SG | LMT | Ops Teams | P0 | 2021-05-01 | Started
Note on J4: Richens, Hannah: as below
Note on J5: Richens, Hannah: list on website and pitch as partnership activities with referral routes
Note on I14: Richens, Hannah: to investigate NHS routes
Note on K20: Richens, Hannah: research into other authorities SRC offer
Note on H22: Richens, Hannah: potentially superceded by HAF and subject to state of pandemic
Note on L24: Richens, Hannah: operational procedures for Kickstart trainees

## Maximise use of the service
Barnet Libraries Team Plan, Objective 3: Maximise the use of the service and its resources
No. | Barnet Plan objective | Barnet Plan objective | BP sub heading | BP sub heading | Team Plan outcome | 3 Rs | What | Who (Lead) | Who | Who | Who | When | Progress | Progress Checks notes For P1 use
1 | All |  | All |  | Integration with other council & community services | Reinvent | Ensure that libraries are part of key corporate startegies | HR |  |  |  | 2020-11-01 | started
2 | All |  | All |  | Integration with other council & community services | Reinvent | Review all committee forward plans to identify synergies | P1 |  |  |  | 2021-01-01 | started
3 | Thriving |  | Growth Strategy |  | Integration with other council & community services | Reinvent | New Hendon Library - include multi-use/ multi-agency space and LCS space | LMT | Ops Team | FPR | HP | 2021-01-01 | started
4 | Clean, Safe and Well-Run |  | Improving customer services |  | Integration with other council & community services | Reinvent | Develop communications strategy and forward plan | SG | CL |  |  | 2020-08-01 | started
5 | Clean, Safe and Well-Run | Thriving | Improving customer services | Growth Strategy | Upgrade Library buildings | Reinvent | Open + v2 roll-out | HR | FPR | Ops Teams | P0 | 2021-03-01 | started
6 | Clean, Safe and Well-Run | Thriving | Improving customer services | Growth Strategy | Upgrade Library buildings | Reinvent | upgrade physical and digital signage/ design standards | HR | FPR | Ops Teams | P2 | 2021-06-01 | Open
7 | Clean, Safe and Well-Run |  | Improving customer services |  | Upgrade Library buildings | Reinvent | Renew visitor counters | SGreen | Ops Team |  |  | 2021-06-01 | Open
8 | Clean, Safe and Well-Run | Thriving | Improving customer services | Growth Strategy | Upgrade Library buildings | Reinvent | ESP Project to upgrade boilers, ventilation and lighting | RP | Ops Teams | Estates |  | 2021-01-01 | started
9 | Clean, Safe and Well-Run |  | Improving customer services |  | staff engagement and skils development | Reinvent | Develop staff training plan (to include skills audit) | RP | P5 |  |  | 2021-05-01 | started
10 | Clean, Safe and Well-Run |  | Improving customer services |  | staff engagement and skils development | Reinvent | Develop annual work plan for Libraries Equalities Allies | RP | Equalities Group |  |  | 2021-05-01 | started
11 | Clean, Safe and Well-Run |  | Improving customer services |  | staff engagement and skils development | Reinvent | Relaunch Libraries Leadership Programme | RP | P5 |  |  | 2021-11-01 | Open
12 | Clean, Safe and Well-Run | Thriving | Improving customer services | Growth Strategy | Upgrade Library buildings | Reinvent | New Burnt Oak Library - work with Boost to focus on employment and skills | LMT | Ops Team | FPR |  | 2021-05-01 | started
Note on M4: Richens, Hannah: and on going
Note on M5: Richens, Hannah: then 1/4ly
Note on I8: Richens, Hannah: business case to capital boards
Note on L8: Richens, Hannah: review opening and closing procedures/ SSO assistance
Note on I9: Richens, Hannah: business case to capital boards
Note on L9: Richens, Hannah: spec foir design of screens